## Sheet1
Stories | R1 Sprint 1 | R1 Sprint 2 | Story Points
27 | Landing Page |  | 6
1 | View Schedule |  | 2
2 |  | Edit Schedule | 4
3 | Contact Info |  | 2
TOTAL | 10 | 4 | 14
15 | Attendance Records |  | 2 | Application Core
10 | Admin DB interaction |  | 8 | Administrator Features
16 | Search Teacher & Stu Profiles |  | 2 | Student Features
21 |  | Teacher Feedback | 4 | Teacher Features
23 |  | Contract Generation | 4 | Additional Features
END SPRINT ONE (R1) |  | END SPRINT ONE (R2)
TOTAL | 12 | 8 | 20
6 | Teacher Selection |  | 1
8 |  | ENG 2nd Language | 2
9 | Instrument Selection Lesson |  | 2
26 |  | Instrument Hire | 16
TOTAL | 3 | 18 | 21
12 | Teacher Availability |  | 4
5 | Student Feedback |  | 4
7 | Guard Contact Info |  | 1
END SPRINT TWO (R1)
TOTAL | 9 | - | 9
11 |  | Report export | 8
24 |  | Invoicing | 16
END SPRINT TWO (R2)
25 |  | Job Applications | 16
13 |  | Instrument Inventory | 6
END SPRINT ONE (R3)
TOTAL | - | 46 | 46
SPRINT TOTALS | 34 | 76
|  | GRAND TOTAL | 110